# Customer Support Knowledge Base Project Plan

Project Plan

| Item | Detail |
| --- | --- |
| Prepared | 23 October 2026 |
| Generated by | Autonomous Document Agent |
| Reference | 40ae6b55 |

# Purpose

Provide a practical, phased execution plan for launching a customer support knowledge base for a 20-person SaaS company within a 6-week timeframe.

## Assumptions

The official project kickoff date is unconfirmed, so the schedule tool uses the next upcoming Monday as the baseline.

Content creation relies on existing product documentation and support ticket history as source material, owned by the Customer Support Lead with a monthly review cadence.

Access controls for the knowledge base management system will be restricted to authorized support and product team members.

All team members dedicated to this project have 25% of their working hours allocated specifically to knowledge base tasks.

# 1. Project Objectives and Scope

The primary objective of this 6-week project is to launch a centralized customer support knowledge base that reduces inbound ticket volume by 20 percent and shortens average first-response times for our 20-person SaaS company. Target audiences include active end-users seeking self-service troubleshooting and internal support agents requiring rapid access to verified documentation.

In-Scope: Migration of existing product documentation, drafting of top 50 anticipated customer support articles, implementation of access controls for authorized support and product team members, and integration with the primary ticketing system.

Out-of-Scope: Multilingual translations during phase one, custom software development of proprietary publishing tools, and customer community forums.

Project Scope and Ownership Matrix (Illustrative)

| Scope Item | In/Out | Owner | Success Metric |
| --- | --- | --- | --- |
| Top 50 Articles | In-Scope | Customer Support Lead | 100 percent drafted by Week 3 |
| Access Controls | In-Scope | Product Team Member | Role-based permissions verified |
| Multilingual Support | Out-of-Scope | N/A | Deferred to future quarters |

# 2. Phased Workflow and Timeline

The knowledge base launch follows a structured 6-week phased workflow spanning from October 26, 2026, to December 6, 2026. This timeline assumes that team members allocate 25% of their working hours to project tasks. Access controls are restricted to authorized support and product team members, and content creation relies on existing product documentation and support ticket history as source material.

6-Week Phased Workflow and Timeline

| Phase Name | Start Date | End Date | Duration |
| --- | --- | --- | --- |
| Discovery & Tool Setup | 26 Oct 2026 | 01 Nov 2026 | 1.0 week |
| Content Audit & Drafting | 02 Nov 2026 | 15 Nov 2026 | 2.0 weeks |
| Review, Formatting & QA | 16 Nov 2026 | 29 Nov 2026 | 2.0 weeks |
| Launch & Post-Launch Monitoring | 30 Nov 2026 | 06 Dec 2026 | 1.0 week |

Discovery & Tool Setup: Configure platform permissions and establish taxonomy.

Content Audit & Drafting: Catalog existing documentation and draft core support articles.

Review, Formatting & QA: Validate technical accuracy, formatting standards, and link integrity.

Launch & Post-Launch Monitoring: Deploy the knowledge base publicly and track initial resolution metrics.

# 3. Ownership and Content Management Workflow

To ensure sustainable maintenance of the customer support knowledge base for the 20-person SaaS company, explicit ownership and operational workflows must be established across the team. Content creation and curation rely on existing product documentation and support ticket history as source material, as noted in the project assumptions. The operational framework below defines specific sources, designated owners, monthly review cadences, and update workflows.

Content Management Ownership and Workflow Matrix (Illustrative)

| Content Source | Designated Owner | Review Cadence | Update Workflow |
| --- | --- | --- | --- |
| Support Ticket History | Customer Support Lead | Monthly | Identify recurring customer issues, draft article, route to Product for technical review, publish. |
| Product Documentation | Product Manager | Bi-weekly | Review release notes, update core feature articles, notify Support Lead of changes. |
| Billing and Account FAQs | Operations Lead | Quarterly | Verify policy accuracy with finance, update static pages, archive outdated terms. |

Content Intake: The Customer Support Lead reviews unresolved or frequent support tickets every Monday to identify emerging knowledge gaps.

Drafting and Review: Owners draft or revise content utilizing the designated templates, ensuring access controls restrict editing to authorized support and product team members.

Quality Check: Before publication, the Product Manager verifies technical accuracy for any functional claims, and the Support Lead validates tone and clarity.

Publishing and Archiving: The finalized article is published to the knowledge base, and any deprecated documentation is moved to an archive folder with a redirect link.

# 4. Success Metrics

To evaluate the operational effectiveness and customer adoption of the new knowledge base, we establish a robust framework of quantifiable success metrics. These indicators track pre- and post-launch performance across support efficiency, search efficacy, and overall customer satisfaction. Because historical baseline data was not provided for this proposal, specific numerical targets below are treated as illustrative figures to be calibrated against actual performance during the first thirty days post-launch.

Post-Launch Success Metrics and Evaluation Framework (Illustrative Targets)

| Metric Name | Target | Measurement Method | Owner | Review Cadence |
| --- | --- | --- | --- | --- |
| Ticket Deflection Rate | 15% reduction | Compare volume of incoming support tickets against active user growth | Customer Support Lead | Monthly |
| Search Success Rate | 70% resolved | Track internal search analytics where queries lead to article views and session end | Product Manager | Bi-weekly |
| CSAT Impact | 85% positive | Survey ratings specifically attached to knowledge base article resolution prompts | Customer Support Lead | Monthly |

Data collection relies on automated reports generated by the knowledge base platform and ticketing system.

Monthly reviews will be conducted by the project team to identify content gaps whenever search success rates drop below the target threshold.

Unresolved search queries will be audited weekly to generate new article requirements.

# 5. Risk Management

To ensure the 6-week knowledge base launch succeeds for our 20-person SaaS company, we have identified and evaluated key operational risks. Risk scores are calculated using the formula score equals likelihood multiplied by impact on a scale from 1 to 25, where Low is 4 or less, Medium is 5 to 9, High is 10 to 16, and Critical is above 16 based on authoritative risk analysis tools.

Project Risk Register and Mitigation Strategies

| Risk Description | Likelihood | Impact | Score | Rating | Mitigation Strategy and Owner |
| --- | --- | --- | --- | --- | --- |
| Low team adoption of the content update workflow | 3 | 4 | 12 | High | Mandate workflow training during week 3 and tie update metrics to weekly support reviews; Owner: Support Lead. |
| Delayed content delivery due to competing support ticket volumes | 4 | 3 | 12 | High | Enforce the 25 percent time allocation rule and defer non-critical ticket responses during peak writing sprints; Owner: Operations Manager. |
| Outdated technical documentation used as source material | 2 | 4 | 8 | Medium | Require product team review sign-off for all drafted articles before final publishing; Owner: Product Manager. |

Each risk owner is responsible for conducting bi-weekly checks against these thresholds during the 6-week execution window. Measurable evidence of risk control includes completion logs for workflow training, adherence to the 25 percent capacity allocation, and documented product sign-offs on all source materials.

# 6. Executive Summary

This executive summary synthesizes the operational strategy for launching a customer support knowledge base for a 20-person SaaS company over a 6-week execution window running from October 26, 2026, to December 6, 2026. Designed to address recurring support bottlenecks, the initiative targets a 20 percent reduction in inbound support tickets and improved first-response times. To maintain practical delivery within the constrained timeline, scope is strictly limited to the top 50 support articles, documentation migration, and role-based access controls, while multilingual translations and community forums remain out of scope for the initial release.

Execution is governed across defined phased workflows, assigning direct accountability for content creation and review to the Customer Support Lead utilizing existing product documentation and support ticket history. Access controls restrict knowledge base management strictly to authorized support and product team members. Success is measured through tracking ticket deflection, search success, and customer satisfaction impact, with quantitative targets treated as illustrative pending baseline data collection. Major project risks are actively mitigated through assigned risk owners, bi-weekly checks, and verified training logs and product sign-offs, ensuring a controlled and sustainable launch.

Project Plan Summary Overview

| Plan Component | Summary Details | Owner / Responsibility |
| --- | --- | --- |
| Objectives and Scope | Top 50 articles, documentation migration, role-based access controls; targeting 20 percent ticket reduction | Customer Support Lead |
| Timeline and Workflow | 6-week execution from October 26, 2026, through December 6, 2026 | Project Team (25% allocated hours) |
| Metrics and Governance | Ticket deflection, search success, CSAT impact; monthly review cadence | Customer Support Lead and Product Manager |
| Risk Management | Mitigation of primary project risks via bi-weekly checks and sign-offs | Assigned Risk Owners |

# Appendix A: Agent execution plan

Plan source: llm. Tasks with no dependencies ran in parallel; each task is traced to the requirements it satisfies.

| ID | Task | Depends on | Requirements | Tools | Status |
| --- | --- | --- | --- | --- | --- |
| T1 | Define Objectives and Scope | - | R1 | - | completed |
| T2 | Phased Timeline and Schedule | - | R2 | schedule | completed |
| T3 | Ownership and Content Workflow | - | R3 | - | completed |
| T4 | Success Metrics Definition | - | R4 | - | completed |
| T5 | Risk Assessment and Mitigation | - | R5 | risk_score | completed |
| T6 | Executive Summary | T1, T2, T3, T4, T5 | R6 | - | completed |

# Appendix B: Requirements traceability

| ID | Requirement | Covered by | Review |
| --- | --- | --- | --- |
| R1 | Define clear, measurable project objectives and scope for the 20-person SaaS company context. | T1 | met |
| R2 | Detail a phased workflow covering 6 weeks of execution. | T2 | met |
| R3 | Assign explicit ownership and operational workflows including source, owner, review cadence, and update workflow. | T3 | met |
| R4 | Establish quantifiable success metrics for launch and post-launch performance. | T4 | met |
| R5 | Identify and score key project risks with mitigation strategies. | T5 | met |
| R6 | Include an executive summary synthesizing all plan components. | T6 | met |

The draft fully meets all six requirements with concrete details, structured tables, and explicit operational workflows.

# Appendix C: Tool calls

| Task | Tool | Arguments | Result |
| --- | --- | --- | --- |
| T2 | schedule | {"phases": [{"name": "Discovery & Tool Setup", "weeks": 1}, {"name": "Content Audit & Drafting", "weeks": 2}, {"name": "Review, Formatting & | {"phases": [{"phase": "Discovery & Tool Setup", "start": "26 Oct 2026", "end": "01 Nov 2026", "weeks": 1.0}, {"phase": "Content Audit & Drafting", "start": "02 Nov 2026", "end": "15 Nov 2026", "weeks"... |
| T5 | risk_score | {"risks": [{"name": "Low team adoption of the content update workflow", "likelihood": 3, "impact": 4}, {"name": "Delayed content delivery du | {"risks": [{"name": "Low team adoption of the content update workflow", "likelihood": 3, "impact": 4, "score": 12, "rating": "High"}, {"name": "Delayed content delivery due to competing support ticket... |